## Overall
Group Members | Student ID | Project Role
Tolga Ertunç | B2280.060052 | Database & Testing
İlke Görkem Şahin | B2180.060042 | Backend Developer
Project Name | Smart Barber Booking System
Overview | The system is a cloud-based platform built on an N-Tier architecture designed to digitize traditional barbershop operations. It features 24/7 online booking, automated notifications, and an AI-powered hairstyle preview module using Python. By leveraging .NET Web API, React 18, and PostgreSQL, the system eliminates double-booking conflicts and improves operational efficiency.
Phases | Timeline | Tasks
Phase 1: Core Infrastructure | Week 1 - 2 | Database schema creation and initial configuration.
| Week 3 | Implementation of the conflict prevention algorithm.
| Week 4 | Coding core API endpoints for authentication and slots.
Phase 2: User Interfaces | Week 5 - 6 | Designing and building the customer booking portal.
| Week 7 - 8 | Developing the admin dashboard for management.
| Week 9 | Integrating responsive design across all devices.
Phase 3: AI Integration | Week 10 - 11 | Integrating the Python image processing service.
| Week 12 - 13 | Implementing photo upload and privacy modules (24h auto-delete).
Phase 4: Testing & Launch | Week 14 - 15 | Unit, Integration, and User Acceptance Testing (UAT).
| Week 16 | Production deployment using Docker containers.
Time Budget | 16 Weeks total development cycle (4 Sprints/Phases). Break-even expected within 6 months of deployment.
Tech Resources | Frontend: React 18, Tailwind CSS.
Backend: .NET Web API (C#), Python (AI Service).
Database & Cache: PostgreSQL, Redis.
Cloud & Deployment: Docker, AWS S3 (Storage).

## Budget Planning
Resource Type | Member | Role | Estimated Hours | Cost per Hour | Total Cost
Development | İlke Ş. | Backend Developer | 70 | 120 | 8400
Development | Tolga E. | Database & Testing | 50 | 100 | 5000
Infrastructure | Cloud Hosting | Cloud Hosting | 720 | 5 | 3600
Total |  |  |  |  | 17000